## T-2421-45-06-01-01-002
SCHEDULE
Name of the work: Extention of 11 KV industrial feeder emanating from 33/11 KV Gadwal New SS which is not in use to bifurcate overloaded 11 KV Town-4 feeder load by erecting 0.88 KM 11 KV line at Krishna river road in operation section Gadwal town in Gadwal Sub-division in Gadwal Division (Under T&D works) WBS No.T-2428-45-01-11-01-001.
|  |  | Face Value |  | 198744
Sl No | Service Code | Description of work | Qty | Unit | Rates per Unit | Amount
1 | SWIP1168 | Survey and tree clearance | 0.88 | LS | 637.5 | 561
2 | SMR11487 | S-MS Bolts & Nuts,Washers etc., | 105 | KG | 91.25 | 9581.25
3 | SWR10356 | Mass concreting of supports incl. cement | 2.715 | M3 | 6579 | 17861.985
4 | SWR11180 | SubTrnsprt 11M PSCC Pole incl. L&UL<10KM | 19 | EA | 431.97 | 8207.43
5 | SWR10109 | EXCAVATION OF PIT(3.0" x 3.0" x 7.6") | 19 | EA | 842.78 | 16012.82
6 | SWR10978 | Errection of 11 M long PSCC pole | 19 | EA | 4165.28 | 79140.32
7 | SWR11308 | Restring-55 Sqmm SC-3 Conductors | 1.04 | KM | 6400 | 6656
8 | SWR10365 | Stringing of 55sqmm 33/11kv Line 3 Cond | 0.88 | KM | 8500 | 7480
9 | SWR11312 | Restring-LT 3-Ph 34Sqmm 5 Conducto | 0.48 | KM | 7200 | 3456
10 | SWR20308 | SubTrnsprt 9M PSCC Pole incl. L&UL<10KM | 6 | EA | 407.29 | 2443.74
11 | SWR10107 | EXCAVATION OF PIT (2.6" x 2.6" x 6.0") | 6 | EA | 700 | 4200
12 | SWR11083 | Erec of 9.1 Mts PSCC poles for stuts | 5 | EA | 2400 | 12000
13 | SWR10308 | FABR-Drilling of holes upto 20 mm dia 5 | 220 | EA | 2 | 440
14 | SWR10294 | Cutting Charges for MS chanl 100x50mm | 44 | EA | 10 | 440
15 | SWR11320 | Dismantle-9.1 M long PSCC pole | 18 | EA | 909.94 | 16378.92
16 | SWR11294 | Erect-intermedi 9.1 M long PSCC pole | 1 | EA | 2728.7 | 2728.7
17 | SWR10393 | Erection of 11kv ABSwitch incl earthing | 1 | EA | 3200 | 3200
18 | SWR10357 | ERECT. OF LINES-Providing of earthing | 1 | EA | 1234.2 | 1234.2
19 | SWR21984 | Ref - Double Jumpering. | 3 | EA | 165 | 495
20 | SWR10653 | Formatn of Horiz Cut point for 11KV line | 1 | EA | 1350 | 1350
21 | SMR11482 | S-CI Pipe earthing 100mm dia 2.75m long | 1 | EA | 3486 | 3486
22 | SMR11488 | S-GI Bolts & Nuts,Washers etc., | 10 | KG | 117.5 | 1175
23 | SWR10151 | TRANSPORT OF STEEL MATERIAL 50 TO 80KM | 0.3 | TO | 718.07 | 215.421
GRAND TOTAL | [5 empty] | 198743.786
Conditions :
1 | The Contractor will have provide his own labour, T&P and Sub-Transport up to 10 km at his cost and above 10 km will be paid as per SSR.
2 | The required materials will be Supplied by the TGSPDCL on free of cost except which are not available matching materials in stores.
3 | The Contractor will be responsible for any accident to any of his workers and liability that may arise for payment of compensation under provision of act of A.P.
4 | The work shall be taken up strictly as per the Seniority and management instructions
5 | Agreement concluded with available SSR-2024-25 codes
6 | Agency which is excavating must use the CBUD App before commencing any excavation on public lands/roads in the state
Signature of the Contractor. |  |  |  | Superintending Engineer I/c
Operation Gadwal.
COMPARATIVE STATEMENT
The Rates quoted by M/s Vijetha Electrical Constructions, Wanaparthy Has Quoted lowest rates. Hence accepted.
Sl No | Service Code | Description of work | Qty | Unit | SSR Rates per Unit
The Rates quoted by Mr. Ravendra Goud, Contractor, K.R.Cheruvu has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. Sreenivasa Goud, Contractor, Shanthinagar has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. E.Nagendra, Contractor, Kurnool has quoted lowest rates. Hence accepted.
The Rates quoted by M/s Vijetha Electricals, Contractor, Wanaparthy has quoted lowest rates. Hence accepted.
The Rates quoted by M/s Harika Electricals, Contractor, Ieeza has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. Praveen Kumar, Contractor, Gadwal has quoted lowest rates. Hence accepted.
| Rates quoted by the Contractor | Amount quoted by the Contractor
Sub-Total:
12.36 % Service tax: | [5 empty] | 0
Total: | [5 empty] | 0
Sri Raghavendra Goud, Civil & Electrical contractor, H. No. 2-21, K.R Cheruvu, Maldakal
Sri E.Nagendra, Contractor, Electrical & Civil Works, H. No. 40-310A, Bhagyanagar, Kurnool
M/s Vijetha Electrical Constructions, H. No. 42-187/6, Vengalrao Colony, Wanaparthy
Sri S.E.Sreenivasa Goud, Contractor, Electrical&Civil Works, Shanthinagar vg., Waddepally M