## Abstract
Abstract Of Works Proposed Under Summer Action Plan 2026 - Suryapet Circle
S.No. | Name Of The Work |  | No. Of Works Proposed |  |  | No. Of Works forword various levels |  |  |  |  | No. Of Works sanction various levels |  |  |  |  | Balance
|  |  | Huzurnagar | Suryapet | Total | Corporate Office | CGM | SE | DE | Total | Corporate Office | CGM | SE | DE | Total
1 | PTRs (Enhancement) (T-2522) | 3.15 - 5.0MVA | 4 | 3 | 7 | 7 |  |  |  | 7 | [5 empty] | 7
|  | 5.0 - 8.0 MVA | 7 | 4 | 11 | 11 |  |  |  | 11 | [5 empty] | 11
|  | TOTAL | 11 | 7 | 18 | 18 |  |  |  | 18 | [5 empty] | 18
2 | PTRs (Addlitional) (T-2521) | 5.0 MVA | 3 | 9 | 12 | 12 |  |  |  | 12 | [5 empty] | 12
|  | TOTAL | 3 | 9 | 12 | 12 |  |  |  | 12 | [5 empty] | 12
3 | 33 Kv Lines Bifurcation Works (T-2530) |  | 3 | 4 | 7 | 7 |  |  |  | 7 | [5 empty] | 7
4 | 33 Kv Lines InterLinking Works (T-2531) |  | 0 | 3 | 3 | 2 |  | 1 |  | 3 |  |  | 1 |  | 1 | 2
5 | 11 Kv Lines Bifurcation Works (T-2532) |  | 6 | 10 | 16 | 6 | 9 | 1 |  | 16 |  | 9 | 1 |  | 10 | 6
6 | 11 Kv Lines InterLinking Works (T-2533) |  | 7 | 4 | 11 |  | 2 | 8 | 1 | 11 |  | 2 | 8 | 1 | 11 | 0
7 | DTRs (Enhancement) (T-2524) | 1Ph-25 KVA | [13 empty] | 0
|  | 3Ph-25KVA | 3 | 0 | 3 |  |  |  | 3 | 3 |  |  |  |  | 0 | 3
|  | 63 KVA | 2 | 17 | 19 |  |  | 8 | 11 | 19 |  |  | 8 |  | 8 | 11
|  | 100 KVA | 21 | 18 | 39 |  |  | 1 | 38 | 39 |  |  | 1 |  | 1 | 38
|  | 160 KVA | 26 | 19 | 45 |  | 13 |  | 32 | 45 |  |  |  |  | 0 | 45
|  | TOTAL | 52 | 54 | 106 | 0 | 13 | 9 | 84 | 106 | 0 | 0 | 0 | 0 | 0 | 97
8 | DTRs (Addlitional) (T-2523) | 1Ph-25 KVA | 201 | 131 | 332 |  |  |  | 332 | 332 |  |  |  |  | 0 | 332
|  | 3Ph-25KVA | 187 | 88 | 275 |  |  | 2 | 273 | 275 |  |  | 2 |  | 2 | 273
|  | 3ph-63KVA | 7 | 69 | 76 |  |  |  | 76 | 76 |  |  |  |  | 0 | 76
|  | 100 KVA | 29 | 18 | 47 |  |  |  | 47 | 47 |  |  |  |  | 0 | 47
|  | 160 KVA | 0 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 0 | 1
|  | TOATL | 424 | 307 | 731 | 0 | 0 | 2 | 729 | 731 | [5 empty] | 729

## 33KV+11KV LINES
1.Bifurcation of 33 KV Lines(2530)
Sl.No | WBS NO. | Description | REMARKS
1 | T-2530-50-01-12-02-001 | Estimate for erection of 2.88KM 33KV new line from 132KV Suryapet SS to bifurcate the loads of 33KV HPCL Feeder (tapping point near Jayashanka polymers) emanating from 132/33KV Suryapet EHT SS in Chivemla section of Suryapet Division in Suryapet Circle under T&D Improvements to original works (Summer Action Plan works-2025). | Agreement under process
2 | T-2530-50-01-12-03-001 | Estimate for erection of 11.57KM 33KV new line from 132KV Suryapet SS to 33/11KV Penpahad SS in order to provide the load relief of 33KV Penpahad feeder emanating from 132/33KV suryapet SS and 33KV nellamri emainting from 132/33 KV munagala SS in penpahad section Suryapet Division of Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | Agreement under process
3 | T-2530-50-01-23-03-001 | Estimate for erection of 2.92Km 33KV New feeder emanating from 132/33KV Nuthankal SS to Errapad X Road tapping point in Nuthankal village to 33KV/11KV Reddygudem SS to bifurcate 33KV Reddygudem feeder emanating from 132/33KV Thungathurthy SS due to 33KV Reddygudem feeder load is 303A in Maddirala section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | Agreement under process
4 | T-2530-50-01-23-02-001 | Estimate for erection of new 16.3Km 33KV Kodur feeder emanating from 132/33KV Nuthankal SS to 33/11KV Kodur Substation to bifurcate the overloaded 335A on 33KV Velugupally feeder emanating from 132/33KV Thungathurthy Substation and through providing of alternate supply to 33/11KV Thallasingaram Substation, Nuthankal Section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T<(>&<)>D Improvement to original works (Summer Action Plan works-2026). | Agreement under process
Total Length of line
2. 33KV Interlinking line(2531)
1 | T-2531-50-01-12-01-002 | Estimate for erection of 6.3KM 33KV interlink line between 33/11KV Nemmikal substation and 33/11KV Athmakur, both are emanating from 132/33KV Nuthankal SS in Athmakur(S) Mandal in Suryapet Division of Suryapet Circle- Under T&D Improvements to Original works (Under Summer Action Plan-2026) | Sent for Sanction/CE/Op/Rural Zone
2 | T-2531-50-01-12-03-002 | Estimate for erection of 33KV Interlink line between 33KV Nelamarry feeder emanating from 132/33KV Munagala EHT SS to 33/11KV Bhakthalapuram SS feeding from 33KV G.Thirualagiri feeder emanating from 132/33KV Munagala EHT SS to provide alternate supply to 33/11KV Bhakthalapuram SS in Penpahad section of Suryapet division in Suryapet Circle - Under T&D Improvements to Original works (Under Summer Action Plan-2026) | Sent for Sanction/CE/Op/Rural Zone
3 | T-2531-50-01-24-01-001 | Estimate Proposal is for erection of IN & OUT arrangement(Alternate Source) to the 33/11KV Adivemla Substation from the 33KV Erkaram Feeder emanating from 132/33KV Suryapet EHT Substation with a distance of 0.77KM line in J.R.Gudem Section of Nagaram Sub-division of Suryapet Division of Suryapet | Agreement under process
Total Length of line
3.Bifurcation of 11 KV lines(2532)
1 | T-2532-50-01-12-03-003 | Estimate for erection of 11kV new Dosapahad 2 feeder from 33/11kV N.Annaram Substation to bifurcate the 11kV Dosapahad &Anajipuram (Penpahad SS )feeder which is over loaded of 196 &171Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. | Agreement under process
2 | T-2532-50-01-12-03-004 | Estimate for erection of 11kV new Gudepukunta thanda feeder from 33/11kV Dupahad Substation to bifurcate the 11kV Nelamarri feeder(Cheedella SS) which is over loaded of 160 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. | Agreement under process
3 | T-2532-50-01-24-01-001 | Estimate for erection of 4.0KM 11KV New Lineproposed in33/11KV Arvapally Substation to bifurcate the loads of 11Kv Parsaipally Feeder emanating from 33/11KV Arvapally Sub-station which is overloaded with Loads of above 160A in J.R.Gudem Section in Suryapet Division under T&D Improvement's works-2026. | Agreement under process
4 | T-2532-50-01-12-03-005 | Estimate for erection of 11kV new Lalsing thanda feeder from 33/11kV Penpahad Substation to bifurcate the 11kV Dubbathanda & Mahmadapuram (Bakthalapuram SS )feeder which is over loaded of 172&155 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. | Agreement under process
5 | T-2532-50-01-12-01-001 | Estimate for erection of additional 11KV bay along with 11kV feeder VCB to formation of 11kV Peepanaik thanda feeder from 33/11kV Patharlapahad Substation to bifurcate the 11kV Gattikal feeder(175Amp) from 33/11KV Kandagatla SS balancing among the PTRs (Crossed 80%) at 33/11KV Kandagatla substation in Athmakur(s) section in Suryapet division in Suryapet Circle under Summer action plan-2026 scheme of T&D budget. | Sent for Sanction/CE/Op/Rural Zone
6 | T-2532-50-01-12-03-002 | Estimate for erection of 11kV new Chetlamukundapuram feeder -2 from 33/11kV Cheedella Substation to bifurcate the 11kV Chetlamukundapuram &New Banjarahills feeder (Doopahad SS) which is over loaded of 171 &175 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. | Agreement under process
7 | T-2532-50-01-24-03-001 | Estimate for Bifurcation of 2.5km 11KV Line Emanating From 33/11KV Nagaram SS in D.Nagaram Section of D.Nagaram Sub-division of Suryapet Circle Under Summer Action Plan -2026 | Agreement under process
8 | T-2532-50-01-11-03-001 | Estimate for erection of additional 11KV bay along with 11kV feeder VCB to formation of 11kV new Dubba Thanda feeder from 33/11kV Yerkaram Substation to bifurcate the 11kV Ramannagudem feeder(145Amp) and 11KV Yerkaram feeder(140Amp) AND load balancing among the PTRs (Crossed 80%) at 33/11KV Yerkaram substation in Suryapet Rural section in Suryapet division in Suryapet Circle under Summer action plan-2026 scheme of T&D budget. | Agreement under process
9 | T-2532-50-01-12-03-001 | Estimate for erection of 11kV new Cheedella Agl 2 feeder from 33/11kV Cheedella Substation to bifurcate the 11kV Cheedella AGL &Thangellagudem feeders which is over loaded of 172&142 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme Under T&D Improvements to Original Works. | Agreement under process
10 | T-2532-50-01-24-01-002 | Estimate for erection of 2.0KM 11KV New Line proposed to bifurcate the loads of 11Kv Timmapuram Feeder emanating from 33/11KV Adivemla Sub-station which is overloaded with Loads of above 160A in J.R.Gudem Section in Suryapet Division under T&D Improvement's works-2026 | Agreement under process
Total Length of line
4. 11KV Interlinking Line(2533)
1 | T-2533-50-01-23-03-001 | Estimate for Erection of 3.0 KM 11KV inter Link Line between 11KV Mamillamadava Feeder and 11KVMukundhapuram feeder in 33/11KV Mukundhapuram SS to divert the loads from 11KV Mamillamadava Feeder to 11KV Mukundhapuram feeder in 33/11KV Mukundhapuram ss in Maddirala section, Suryapet division of Suryapet Circle under T&D improvements to original Works. | Agreement under process
2 | T-2533-50-01-23-01-001 | Estimate for Erection of 1.70 KM 11KV inter Link Line between 11KV Bandaramaram Feeder and 11KV Pasnoor feeder to divert the loads from 11KV Bandaramaram Feeder to 11KV Pasnoor feeder in 33/11KV Thungathurthy ss in Thungathurthy section, Suryapet division of Suryapet Circle under T&D improvements to original Works. | Agreement under process
3 | T-2533-50-01-23-02-001 | Estimate for Erection of 1.1KM 11KV inter Link Line between 11KV Miryala Feeder and 11KV Lingampally feeder to divert the loads from 11KV Lingampally Feeder, 11KV Nuthankal Agl. feeder to tag on 11KV Miryala feeder in 33/11KV Dirisinapally ss in Nuthankal section, Suryapet division of Suryapet Circle under T&D improvements to original Works. | SE/Agreement
4 | T-2533-50-01-23-01-002 | Estimate for Erection of 0.400 KM 11KV inter Link Line between 11KV Manapuram Feeder and 11KV Ravulapally feeder to divert the loads from 11KV Manapuram Feeder and 11KV Ravulapally feeder 33/11KV Ravulapally ss in Thungathurthy section, Suryapet division of Suryapet Circle under T&D improvements to original Works. | SE/Agreement
Total Length of line

## DTRs
ADDITIONAL
Sl.No | 1-ph 10kva | 1-ph 15kva | 1-ph 25KVA | 3-25KVA | 63 KVA | 100 KVA | TOTAL
1 | 3 | 5 | 68 | 83 | 34 | 11 | 204
ENHANCEMENT
Sl.No | 1-ph 25KVA | 3-25KVA | 63 KVA | 100 KVA | 160 KVA | TOTAL
1 | 3 | 2 | 9 | 8 | 13 | 35

## PTR'S
1.Enhancement of PTRs
SL.NO | WBS NO | Name of the work | REMARKS
1 | T-2522-50-01-12-02-002 | Estimate for enhancement of PTR-III Capacity from Existing 3.15MVA to 5MVA i.e., from existing 2X8+ 1X 3.15 MVA to 2x8+1x5 MVA at 33/11KV chandupatla SS in Chivemula Section of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2026). | Under tender process
2 | T-2522-50-01-12-02-001 | Estimate for enhancement of PTR-I Capacity from Existing 5MVA to 8MVA i.e., from existing 2X5MVA to 1x5+ 1x8 MVA at 33/11KV Durajpally SS in Chivemula Section of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2026). | Under tender process
3 | T-2522-50-01-11-03-001 | Estimate for enhancement of existing PTR-I capacity from 5MVA to 8MVA i.e., from existing 1X8+1X5 MVA to 2X8MVA at 33/11KV Yerkaram Substation in Suryapet Mandal of Suryapet Rural section of Suryapet Division of Suryapet Circle under summer action plan 2025-26. | Under tender process
4 | T-2522-50-01-24-02-001 | Estimate for enhancement of PTR-II Capacity from existing 3.15MVA to 5MVA i.e., from existing 1X5 MVA+1X3.15 to 2X5MVA PTRs at 33/11 KV Thatipamula Sub-station in Operation section Thirumalagiri of D.Nagaram sub-division of Suryapet Division of Suryapet Circle Under T&D PTR augmentation works (Summer Action Plan Works-2026). | Under tender process
5 | T-2522-50-01-24-02-002 | Estimate for enhancement of PTR-II Capacity from existing 5MVA to 8MVA i.e., from existing 2X5 MVA to1X5+1X8MVA PTRs at 33/11 KV Gundepuri Sub-station in Operation section Thirumalagiri of D.Nagaram sub-division of Suryapet Division of Suryapet Circle – Under T&D PTR augmentation works (Summer Action Plan Works-2026) | Under tender process
6 | T-2522-50-01-12-01-001 | Estimate for enhancement of PTR-II Capacity from 3.15MVA to 5MVA i.e., from existing 1X5+1X3.15MVA to 2X5 MVA at 33/11KV Patharlpahad SS in Athmakur(s) Mandal of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2025). | Under tender process
7 | T-2522-50-01-12-01-002 | Estimate for enhancement of PTR-I Capacity from 5MVA to 8MVA i.e., from existing 1X5MVA+1X8MVA to 2X8 MVA at 33/11KV Kandagatla SS in Athmakur(s) Section of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2026). | Under tender process
2.Additional PTRs
1 | T-2521-50-01-24-01-001 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVA PTRs in 33/11KV Arvapally Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works (Summer Action Plan Works-2026) | Under tender process
2 | T-2521-50-01-24-01-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Kodur Sub-station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle- Under T&D PTR augmentation works (Summer Action Plan Works-2026) | Under tender process
3 | T-2521-50-01-24-01-003 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Adivemla Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works Summer action Plan-2026) | Under tender process
4 | T-2521-50-01-12-03-002 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 2X8MVA PTRs thus making a total capacity of 2X8MVA + 1X5 MVA at 33/11KV Penpahad SS in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works.(Summer Action Plan-2026) | Under tender process
5 | T-2521-50-01-12-03-003 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 1X5MVA+ 1X8 MVA PTRs thus making a total capacity of 2X5MVA + 1X8 MVA at 33/11KV N.Annaram Sub-station in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works (Summer Action Plan-2026). | Under tender process
6 | T-2521-50-01-24-02-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVAPTRs in 33/11KV Jalalpuram Sub-Station in Operation section Thirumalagiri of Nagaram sub-division of Suryapet Division of Suryapet Circle -Under T&D PTR Augumentation works (Summer Action Plan Works - 2026) | Under tender process
7 | T-2521-50-01-24-03-001 | Estimate for Erection of 1No. additional 5MVA PTR to the Existing 2X8MVA PTR'S thus making a total capacity of 1X5+2X8MVA at 33/11KV Nagaram Sub-Station in D.Nagaram Section of D.Nagaram Sub-division in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works ( Summer Action Plan-2026). | Under tender process
8 | T-2521-50-01-12-01-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 1X8MVA + 1X5 MVA PTRs thus making a total capacity of 1x8+2X5MVA at 33/11KV Aipoor Sub-station in Operation Section Athmakur(s) of Operation Sub-Division Suryapet Rural of Operation Division Suryapet of Suryapet Circle under 3T&D PTR Augmentation works (Summer action plan-2026) | Under tender process
9 | T-2521-50-01-12-03-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 2X8MVA PTR thus making a total capacity of 2X8+1X5MVA PTRs at 33/11KV Cheedella Sub-station in Operation Section Penpahad of Operation Sub-Division Suryapet Rural in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works. | Under tender process | u

## PTR'S with cost
1.Enhancement of PTRs
SL.NO | WBS NO | Name of the work | Service Cost | Material Cost | REMARKS
1 | T-2522-50-01-12-02-002 | Estimate for enhancement of PTR-III Capacity from Existing 3.15MVA to 5MVA i.e., from existing 2X8+ 1X 3.15 MVA to 2x8+1x5 MVA at 33/11KV chandupatla SS in Chivemula Section of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2026). | 0 | 7916856.25
2 | T-2522-50-01-12-02-001 | Estimate for enhancement of PTR-I Capacity from Existing 5MVA to 8MVA i.e., from existing 2X5MVA to 1x5+ 1x8 MVA at 33/11KV Durajpally SS in Chivemula Section of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2026). | 0 | 9801101.42
3 | T-2522-50-01-11-03-001 | Estimate for enhancement of existing PTR-I capacity from 5MVA to 8MVA i.e., from existing 1X8+1X5 MVA to 2X8MVA at 33/11KV Yerkaram Substation in Suryapet Mandal of Suryapet Rural section of Suryapet Division of Suryapet Circle under summer action plan 2025-26. | 0 | 9801101.42
4 | T-2522-50-01-24-02-001 | Estimate for enhancement of PTR-II Capacity from existing 3.15MVA to 5MVA i.e., from existing 1X5 MVA+1X3.15 to 2X5MVA PTRs at 33/11 KV Thatipamula Sub-station in Operation section Thirumalagiri of D.Nagaram sub-division of Suryapet Division of Suryapet Circle Under T&D PTR augmentation works (Summer Action Plan Works-2026). | 0 | 7916856.25
5 | T-2522-50-01-24-02-002 | Estimate for enhancement of PTR-II Capacity from existing 5MVA to 8MVA i.e., from existing 2X5 MVA to1X5+1X8MVA PTRs at 33/11 KV Gundepuri Sub-station in Operation section Thirumalagiri of D.Nagaram sub-division of Suryapet Division of Suryapet Circle – Under T&D PTR augmentation works (Summer Action Plan Works-2026) | 0 | 9801101.42 | Under tender process
6 | T-2522-50-01-12-01-001 | Estimate for enhancement of PTR-II Capacity from 3.15MVA to 5MVA i.e., from existing 1X5+1X3.15MVA to 2X5 MVA at 33/11KV Patharlpahad SS in Athmakur(s) Mandal of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2025). | 0 | 7916856.25 | Under tender process
7 | T-2522-50-01-12-01-002 | Estimate for enhancement of PTR-I Capacity from 5MVA to 8MVA i.e., from existing 1X5MVA+1X8MVA to 2X8 MVA at 33/11KV Kandagatla SS in Athmakur(s) Section of Suryapet Rural Sub-division of Suryapet Division of Suryapet Circle under T&D PTR Augmentation works (Summer Action Plan works-2026). | 0 | 9801101.42 | Under tender process
2.Additional PTRs
1 | T-2521-50-01-24-01-001 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVA PTRs in 33/11KV Arvapally Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works (Summer Action Plan Works-2026) | 563982.46 |  | Under tender process
2 | T-2521-50-01-24-01-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Kodur Sub-station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle- Under T&D PTR augmentation works (Summer Action Plan Works-2026) | 419769.12 |  | Under tender process
3 | T-2521-50-01-24-01-003 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Adivemla Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works Summer action Plan-2026) | 459424.74 |  | Under tender process
4 | T-2521-50-01-12-03-002 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 2X8MVA PTRs thus making a total capacity of 2X8MVA + 1X5 MVA at 33/11KV Penpahad SS in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works.(Summer Action Plan-2026) | 452018.55 |  | Under tender process
5 | T-2521-50-01-12-03-003 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 1X5MVA+ 1X8 MVA PTRs thus making a total capacity of 2X5MVA + 1X8 MVA at 33/11KV N.Annaram Sub-station in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works (Summer Action Plan-2026). | 452014.65 |  | Under tender process
6 | T-2521-50-01-24-02-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVAPTRs in 33/11KV Jalalpuram Sub-Station in Operation section Thirumalagiri of Nagaram sub-division of Suryapet Division of Suryapet Circle -Under T&D PTR Augumentation works (Summer Action Plan Works - 2026) | 458715.6 |  | Under tender process
7 | T-2521-50-01-24-03-001 | Estimate for Erection of 1No. additional 5MVA PTR to the Existing 2X8MVA PTR'S thus making a total capacity of 1X5+2X8MVA at 33/11KV Nagaram Sub-Station in D.Nagaram Section of D.Nagaram Sub-division in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works ( Summer Action Plan-2026). | 511351.22 |  | Under tender process
8 | T-2521-50-01-12-01-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 1X8MVA + 1X5 MVA PTRs thus making a total capacity of 1x8+2X5MVA at 33/11KV Aipoor Sub-station in Operation Section Athmakur(s) of Operation Sub-Division Suryapet Rural of Operation Division Suryapet of Suryapet Circle under 3T&D PTR Augmentation works (Summer action plan-2026) | 722189.2 |  | SE Level
9 | T-2521-50-01-12-03-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 2X8MVA PTR thus making a total capacity of 2X8+1X5MVA PTRs at 33/11KV Cheedella Sub-station in Operation Section Penpahad of Operation Sub-Division Suryapet Rural in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works. | 756199.06 |  | SE Level | u

## 33KV+11KV LINES cost
1.Bifurcation of 33 KV Lines(2530)
Sl.No | WBS NO. | Description | Service Cost | REMARKS
1 | T-2530-50-01-12-02-001 | Estimate for erection of 2.88KM 33KV new line from 132KV Suryapet SS to bifurcate the loads of 33KV HPCL Feeder (tapping point near Jayashanka polymers) emanating from 132/33KV Suryapet EHT SS in Chivemla section of Suryapet Division in Suryapet Circle under T&D Improvements to original works (Summer Action Plan works-2025). | 516481.92 | Agreement under process
2 | T-2530-50-01-12-03-001 | Estimate for erection of 11.57KM 33KV new line from 132KV Suryapet SS to 33/11KV Penpahad SS in order to provide the load relief of 33KV Penpahad feeder emanating from 132/33KV suryapet SS and 33KV nellamri emainting from 132/33 KV munagala SS in penpahad section Suryapet Division of Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | 1520715.11 | Agreement under process
4 | T-2530-50-01-23-02-001 | Estimate for erection of new 16.3Km 33KV Kodur feeder emanating from 132/33KV Nuthankal SS to 33/11KV Kodur Substation to bifurcate the overloaded 335A on 33KV Velugupally feeder emanating from 132/33KV Thungathurthy Substation and through providing of alternate supply to 33/11KV Thallasingaram Substation, Nuthankal Section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T<(>&<)>D Improvement to original works (Summer Action Plan works-2026). | 1480791.96 | Agreement under process
Total Length of line
2. 33KV Interlinking line(2531)
1 | T-2531-50-01-12-01-002 | Estimate for erection of 6.3KM 33KV interlink line between 33/11KV Nemmikal substation and 33/11KV Athmakur, both are emanating from 132/33KV Nuthankal SS in Athmakur(S) Mandal in Suryapet Division of Suryapet Circle- Under T&D Improvements to Original works (Under Summer Action Plan-2026) | 1088085.18 | Sent for Sanction/CE/Op/Rural Zone
2 | T-2531-50-01-12-03-002 | Estimate for erection of 33KV Interlink line between 33KV Nelamarry feeder emanating from 132/33KV Munagala EHT SS to 33/11KV Bhakthalapuram SS feeding from 33KV G.Thirualagiri feeder emanating from 132/33KV Munagala EHT SS to provide alternate supply to 33/11KV Bhakthalapuram SS in Penpahad section of Suryapet division in Suryapet Circle - Under T&D Improvements to Original works (Under Summer Action Plan-2026) | 570745.65 | Sent for Sanction/CE/Op/Rural Zone
3 | T-2531-50-01-24-01-001 | Estimate Proposal is for erection of IN & OUT arrangement(Alternate Source) to the 33/11KV Adivemla Substation from the 33KV Erkaram Feeder emanating from 132/33KV Suryapet EHT Substation with a distance of 0.77KM line in J.R.Gudem Section of Nagaram Sub-division of Suryapet Division of Suryapet |  | Agreement under process
Total Length of line
3.Bifurcation of 11 KV lines(2532)
1 | T-2532-50-01-12-03-003 | Estimate for erection of 11kV new Dosapahad 2 feeder from 33/11kV N.Annaram Substation to bifurcate the 11kV Dosapahad &Anajipuram (Penpahad SS )feeder which is over loaded of 196 &171Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. |  | Agreement under process
2 | T-2532-50-01-12-03-004 | Estimate for erection of 11kV new Gudepukunta thanda feeder from 33/11kV Dupahad Substation to bifurcate the 11kV Nelamarri feeder(Cheedella SS) which is over loaded of 160 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. |  | Agreement under process
3 | T-2532-50-01-24-01-001 | Estimate for erection of 4.0KM 11KV New Lineproposed in33/11KV Arvapally Substation to bifurcate the loads of 11Kv Parsaipally Feeder emanating from 33/11KV Arvapally Sub-station which is overloaded with Loads of above 160A in J.R.Gudem Section in Suryapet Division under T&D Improvement's works-2026. |  | Agreement under process
4 | T-2532-50-01-12-03-005 | Estimate for erection of 11kV new Lalsing thanda feeder from 33/11kV Penpahad Substation to bifurcate the 11kV Dubbathanda & Mahmadapuram (Bakthalapuram SS )feeder which is over loaded of 172&155 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. |  | Agreement under process
5 | T-2532-50-01-12-01-001 | Estimate for erection of additional 11KV bay along with 11kV feeder VCB to formation of 11kV Peepanaik thanda feeder from 33/11kV Patharlapahad Substation to bifurcate the 11kV Gattikal feeder(175Amp) from 33/11KV Kandagatla SS balancing among the PTRs (Crossed 80%) at 33/11KV Kandagatla substation in Athmakur(s) section in Suryapet division in Suryapet Circle under Summer action plan-2026 scheme of T&D budget. |  | Sent for Sanction/CE/Op/Rural Zone
6 | T-2532-50-01-12-03-002 | Estimate for erection of 11kV new Chetlamukundapuram feeder -2 from 33/11kV Cheedella Substation to bifurcate the 11kV Chetlamukundapuram &New Banjarahills feeder (Doopahad SS) which is over loaded of 171 &175 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme of T&D budget. |  | Agreement under process
7 | T-2532-50-01-24-03-001 | Estimate for Bifurcation of 2.5km 11KV Line Emanating From 33/11KV Nagaram SS in D.Nagaram Section of D.Nagaram Sub-division of Suryapet Circle Under Summer Action Plan -2026 |  | Agreement under process
8 | T-2532-50-01-11-03-001 | Estimate for erection of additional 11KV bay along with 11kV feeder VCB to formation of 11kV new Dubba Thanda feeder from 33/11kV Yerkaram Substation to bifurcate the 11kV Ramannagudem feeder(145Amp) and 11KV Yerkaram feeder(140Amp) AND load balancing among the PTRs (Crossed 80%) at 33/11KV Yerkaram substation in Suryapet Rural section in Suryapet division in Suryapet Circle under Summer action plan-2026 scheme of T&D budget. |  | Agreement under process
9 | T-2532-50-01-12-03-001 | Estimate for erection of 11kV new Cheedella Agl 2 feeder from 33/11kV Cheedella Substation to bifurcate the 11kV Cheedella AGL &Thangellagudem feeders which is over loaded of 172&142 Amps in Penpahad section in Suryapet division in Suryapet Circle under Summer action plan-2025 scheme Under T&D Improvements to Original Works. |  | Agreement under process
10 | T-2532-50-01-24-01-002 | Estimate for erection of 2.0KM 11KV New Line proposed to bifurcate the loads of 11Kv Timmapuram Feeder emanating from 33/11KV Adivemla Sub-station which is overloaded with Loads of above 160A in J.R.Gudem Section in Suryapet Division under T&D Improvement's works-2026 |  | Agreement under process
Total Length of line
4. 11KV Interlinking Line(2533)
1 | T-2533-50-01-23-03-001 | Estimate for Erection of 3.0 KM 11KV inter Link Line between 11KV Mamillamadava Feeder and 11KVMukundhapuram feeder in 33/11KV Mukundhapuram SS to divert the loads from 11KV Mamillamadava Feeder to 11KV Mukundhapuram feeder in 33/11KV Mukundhapuram ss in Maddirala section, Suryapet division of Suryapet Circle under T&D improvements to original Works. |  | Agreement under process
2 | T-2533-50-01-23-01-001 | Estimate for Erection of 1.70 KM 11KV inter Link Line between 11KV Bandaramaram Feeder and 11KV Pasnoor feeder to divert the loads from 11KV Bandaramaram Feeder to 11KV Pasnoor feeder in 33/11KV Thungathurthy ss in Thungathurthy section, Suryapet division of Suryapet Circle under T&D improvements to original Works. |  | Agreement under process
3 | T-2533-50-01-23-02-001 | Estimate for Erection of 1.1KM 11KV inter Link Line between 11KV Miryala Feeder and 11KV Lingampally feeder to divert the loads from 11KV Lingampally Feeder, 11KV Nuthankal Agl. feeder to tag on 11KV Miryala feeder in 33/11KV Dirisinapally ss in Nuthankal section, Suryapet division of Suryapet Circle under T&D improvements to original Works. |  | SE/Agreement
4 | T-2533-50-01-23-01-002 | Estimate for Erection of 0.400 KM 11KV inter Link Line between 11KV Manapuram Feeder and 11KV Ravulapally feeder to divert the loads from 11KV Manapuram Feeder and 11KV Ravulapally feeder 33/11KV Ravulapally ss in Thungathurthy section, Suryapet division of Suryapet Circle under T&D improvements to original Works. |  | SE/Agreement
Total Length of line

## PTR'S with cost (2)
Sl.No. |  | WBS NO | Name of the work | Service Cost | ESTIMATE STATUS | Remarks
1. 33KV Bifurcation (2530)
1 | 22.11.2025 | T-2530-50-01-12-02-001 | Estimate for erection of 2.88KM 33KV new line from 132KV Suryapet SS to bifurcate the loads of 33KV HPCL Feeder (tapping point near Jayashanka polymers) emanating from 132/33KV Suryapet EHT SS in Chivemla section of Suryapet Division in Suryapet Circle under T&D Improvements to original works (Summer Action Plan works-2025). | 516481.92 | APPROVED | DE/TENDER PROCESS
2 | 02.12.2025 | T-2530-50-01-23-03-001 | Estimate for erection of 2.92Km 33KV New feeder emanating from 132/33KV Nuthankal SS to Errapad X Road tapping point in Nuthankal village to 33KV/11KV Reddygudem SS to bifurcate 33KV Reddygudem feeder emanating from 132/33KV Thungathurthy SS due to 33KV Reddygudem feeder load is 303A in Maddirala section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | 535439.25 | APPROVED | DE/TENDER PROCESS
2. 33KV Interlinking line(2531)
3 | 15.12.2025 | T-2531-50-01-12-03-002 | Estimate for erection of 33KV Interlink line between 33KV Nelamarry feeder emanating from 132/33KV Munagala EHT SS to 33/11KV Bhakthalapuram SS feeding from 33KV G.Thirualagiri feeder emanating from 132/33KV Munagala EHT SS to provide alternate supply to 33/11KV Bhakthalapuram SS in Penpahad section of Suryapet division in Suryapet Circle - Under T&D Improvements to Original works (Under Summer Action Plan-2026) | 570745.65 | APPROVED | DE/TENDER PROCESS
3. Additional PTRs
4 | 19.11.2025 | T-2521-50-01-24-01-001 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVA PTRs in 33/11KV Arvapally Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works (Summer Action Plan Works-2026) | 563982.46 | APPROVED | DE/TENDER PROCESS
5 | 17.11.2025 | T-2521-50-01-24-01-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Kodur Sub-station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle- Under T&D PTR augmentation works (Summer Action Plan Works-2026) | 419769.12 | APPROVED | DE/TENDER PROCESS
6 | 19.11.2025 | T-2521-50-01-24-01-003 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Adivemla Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works Summer action Plan-2026) | 459424.74 | APPROVED | DE/TENDER PROCESS
7 | 19.11.2025 | T-2521-50-01-12-03-002 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 2X8MVA PTRs thus making a total capacity of 2X8MVA + 1X5 MVA at 33/11KV Penpahad SS in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works.(Summer Action Plan-2026) | 452018.55 | APPROVED | DE/TENDER PROCESS
8 | 17.11.2025 | T-2521-50-01-12-03-003 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 1X5MVA+ 1X8 MVA PTRs thus making a total capacity of 2X5MVA + 1X8 MVA at 33/11KV N.Annaram Sub-station in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works (Summer Action Plan-2026). | 452014.65 | APPROVED | DE/TENDER PROCESS
9 | 19.11.2025 | T-2521-50-01-24-02-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVAPTRs in 33/11KV Jalalpuram Sub-Station in Operation section Thirumalagiri of Nagaram sub-division of Suryapet Division of Suryapet Circle -Under T&D PTR Augumentation works (Summer Action Plan Works - 2026) | 458715.6 | APPROVED | DE/TENDER PROCESS
10 | 29.11.2025 | T-2521-50-01-24-03-001 | Estimate for Erection of 1No. additional 5MVA PTR to the Existing 2X8MVA PTR'S thus making a total capacity of 1X5+2X8MVA at 33/11KV Nagaram Sub-Station in D.Nagaram Section of D.Nagaram Sub-division in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works ( Summer Action Plan-2026). | 511351.22 | APPROVED | DE/TENDER PROCESS
11 | 06.12.2025 | T-2521-50-01-12-01-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 1X8MVA + 1X5 MVA PTRs thus making a total capacity of 1x8+2X5MVA at 33/11KV Aipoor Sub-station in Operation Section Athmakur(s) of Operation Sub-Division Suryapet Rural of Operation Division Suryapet of Suryapet Circle under 3T&D PTR Augmentation works (Summer action plan-2026) | 722189.2 | APPROVED | DE/TENDER PROCESS
12 | 29.11.2025 | T-2521-50-01-12-03-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 2X8MVA PTR thus making a total capacity of 2X8+1X5MVA PTRs at 33/11KV Cheedella Sub-station in Operation Section Penpahad of Operation Sub-Division Suryapet Rural in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works. | 756199.06 | APPROVED | DE/TENDER PROCESS
13 |  | T-2532-50-01-12-01-001 | Estimate for erection of additional 11KV bay along with 11kV feeder VCB to formation of 11kV Peepanaik thanda feeder from 33/11kV Patharlapahad Substation to bifurcate the 11kV Gattikal feeder(175Amp) from 33/11KV Kandagatla SS balancing among the PTRs (Crossed 80%) at 33/11KV Kandagatla substation in Athmakur(s) section in Suryapet division in Suryapet Circle under Summer action plan-2026 scheme of T&D budget. | 340611 | NOT APPROVED | DE/TENDER PROCESS
14 |  | T-2531-50-01-12-01-002 | Estimate for erection of 6.3KM 33KV interlink line between 33/11KV Nemmikal substation and 33/11KV Athmakur, both are emanating from 132/33KV Nuthankal SS in Athmakur(S) Mandal in Suryapet Division of Suryapet Circle- Under T&D Improvements to Original works (Under Summer Action Plan-2026) | 1088085.18 | APPROVED | SE/TENDER PROCESS
15 |  | T-2530-50-01-12-03-001 | Estimate for erection of 11.57KM 33KV new line from 132KV Suryapet SS to 33/11KV Penpahad SS in order to provide the load relief of 33KV Penpahad feeder emanating from 132/33KV suryapet SS and 33KV nellamri emainting from 132/33 KV munagala SS in penpahad section Suryapet Division of Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | 1520716 | APPROVED | CE/TENDER PROCESS
16 |  | T-2530-50-01-23-02-001 | Estimate for erection of new 16.3Km 33KV Kodur feeder emanating from 132/33KV Nuthankal SS to 33/11KV Kodur Substation to bifurcate the overloaded 335A on 33KV Velugupally feeder emanating from 132/33KV Thungathurthy Substation and through providing of alternate supply to 33/11KV Thallasingaram Substation, Nuthankal Section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T<(>&<)>D Improvement to original works (Summer Action Plan works-2026). | 2632782 | APPROVED | CE/TENDER PROCESS

## PTR'S with cost (3)
Sl.No. |  | WBS NO | Name of the work | Service Cost | ESTIMATE STATUS | Remarks
1 | 22.11.2025 | T-2530-50-01-12-02-001 | Estimate for erection of 2.88KM 33KV new line from 132KV Suryapet SS to bifurcate the loads of 33KV HPCL Feeder (tapping point near Jayashanka polymers) emanating from 132/33KV Suryapet EHT SS in Chivemla section of Suryapet Division in Suryapet Circle under T&D Improvements to original works (Summer Action Plan works-2025). | 516481.92 | APPROVED | DE/TENDER PROCESS
2 | 02.12.2025 | T-2530-50-01-23-03-001 | Estimate for erection of 2.92Km 33KV New feeder emanating from 132/33KV Nuthankal SS to Errapad X Road tapping point in Nuthankal village to 33KV/11KV Reddygudem SS to bifurcate 33KV Reddygudem feeder emanating from 132/33KV Thungathurthy SS due to 33KV Reddygudem feeder load is 303A in Maddirala section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | 535439.25 | APPROVED | DE/TENDER PROCESS
3 | 15.12.2025 | T-2531-50-01-12-03-002 | Estimate for erection of 33KV Interlink line between 33KV Nelamarry feeder emanating from 132/33KV Munagala EHT SS to 33/11KV Bhakthalapuram SS feeding from 33KV G.Thirualagiri feeder emanating from 132/33KV Munagala EHT SS to provide alternate supply to 33/11KV Bhakthalapuram SS in Penpahad section of Suryapet division in Suryapet Circle - Under T&D Improvements to Original works (Under Summer Action Plan-2026) | 570745.65 | APPROVED | DE/TENDER PROCESS
4 | 19.11.2025 | T-2521-50-01-24-01-001 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVA PTRs in 33/11KV Arvapally Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works (Summer Action Plan Works-2026) | 563982.46 | APPROVED | DE/TENDER PROCESS
5 | 17.11.2025 | T-2521-50-01-24-01-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Kodur Sub-station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle- Under T&D PTR augmentation works (Summer Action Plan Works-2026) | 419769.12 | APPROVED | DE/TENDER PROCESS
6 | 19.11.2025 | T-2521-50-01-24-01-003 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Adivemla Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works Summer action Plan-2026) | 459424.74 | APPROVED | DE/TENDER PROCESS
7 | 19.11.2025 | T-2521-50-01-12-03-002 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 2X8MVA PTRs thus making a total capacity of 2X8MVA + 1X5 MVA at 33/11KV Penpahad SS in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works.(Summer Action Plan-2026) | 452018.55 | APPROVED | DE/TENDER PROCESS
8 | 17.11.2025 | T-2521-50-01-12-03-003 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 1X5MVA+ 1X8 MVA PTRs thus making a total capacity of 2X5MVA + 1X8 MVA at 33/11KV N.Annaram Sub-station in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works (Summer Action Plan-2026). | 452014.65 | APPROVED | DE/TENDER PROCESS
9 | 19.11.2025 | T-2521-50-01-24-02-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVAPTRs in 33/11KV Jalalpuram Sub-Station in Operation section Thirumalagiri of Nagaram sub-division of Suryapet Division of Suryapet Circle -Under T&D PTR Augumentation works (Summer Action Plan Works - 2026) | 458715.6 | APPROVED | DE/TENDER PROCESS
10 | 29.11.2025 | T-2521-50-01-24-03-001 | Estimate for Erection of 1No. additional 5MVA PTR to the Existing 2X8MVA PTR'S thus making a total capacity of 1X5+2X8MVA at 33/11KV Nagaram Sub-Station in D.Nagaram Section of D.Nagaram Sub-division in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works ( Summer Action Plan-2026). | 511351.22 | APPROVED | DE/TENDER PROCESS
11 | 06.12.2025 | T-2521-50-01-12-01-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 1X8MVA + 1X5 MVA PTRs thus making a total capacity of 1x8+2X5MVA at 33/11KV Aipoor Sub-station in Operation Section Athmakur(s) of Operation Sub-Division Suryapet Rural of Operation Division Suryapet of Suryapet Circle under 3T&D PTR Augmentation works (Summer action plan-2026) | 722189.2 | APPROVED | DE/TENDER PROCESS
12 | 29.11.2025 | T-2521-50-01-12-03-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 2X8MVA PTR thus making a total capacity of 2X8+1X5MVA PTRs at 33/11KV Cheedella Sub-station in Operation Section Penpahad of Operation Sub-Division Suryapet Rural in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works. | 756199.06 | APPROVED | DE/TENDER PROCESS
13 |  | T-2532-50-01-12-01-001 | Estimate for erection of additional 11KV bay along with 11kV feeder VCB to formation of 11kV Peepanaik thanda feeder from 33/11kV Patharlapahad Substation to bifurcate the 11kV Gattikal feeder(175Amp) from 33/11KV Kandagatla SS balancing among the PTRs (Crossed 80%) at 33/11KV Kandagatla substation in Athmakur(s) section in Suryapet division in Suryapet Circle under Summer action plan-2026 scheme of T&D budget. | 340611 | NOT APPROVED | DE/TENDER PROCESS

## PTR'S with cost (4)
Sl.No. | Sp.No. | CAT | WBS NO | Name of the work | Service Cost | 2% SD
1 | 29 | Others | T-2521-50-01-24-01-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Kodur Sub-station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle- Under T&D PTR augmentation works (Summer Action Plan Works-2026) | 419769.12 | 8395.3824
2 | 30 | Others | T-2521-50-01-12-03-003 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 1X5MVA+ 1X8 MVA PTRs thus making a total capacity of 2X5MVA + 1X8 MVA at 33/11KV N.Annaram Sub-station in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works (Summer Action Plan-2026). | 452014.65 | 9040.293
3 | 31 | Others | T-2521-50-01-12-03-002 | Estimate for erection of 1No. Additional 5MVA PTR to the existing 2X8MVA PTRs thus making a total capacity of 2X8MVA + 1X5 MVA at 33/11KV Penpahad SS in Penpahad section of Suryapet Rural Sub-division in Suryapet division of Suryapet Circle - Under PTR Augmentation works.(Summer Action Plan-2026) | 452018.55 | 9040.371
4 | 32 | Others | T-2521-50-01-24-01-001 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVA PTRs in 33/11KV Arvapally Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works (Summer Action Plan Works-2026) | 563982.46 | 11279.6492
5 | 33 | ST | T-2521-50-01-12-01-001 | Estimate for erection of 1No. additional 5MVA PTR to the existing 1X8MVA + 1X5 MVA PTRs thus making a total capacity of 1x8+2X5MVA at 33/11KV Aipoor Sub-station in Operation Section Athmakur(s) of Operation Sub-Division Suryapet Rural of Operation Division Suryapet of Suryapet Circle under 3T&D PTR Augmentation works (Summer action plan-2026) | 722189.2 | 14443.784
6 | 34 | Others | T-2521-50-01-24-02-002 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 2x8MVAPTRs in 33/11KV Jalalpuram Sub-Station in Operation section Thirumalagiri of Nagaram sub-division of Suryapet Division of Suryapet Circle -Under T&D PTR Augumentation works (Summer Action Plan Works - 2026) | 458715.6 | 9174.312
7 | 35 | Others | T-2530-50-01-12-02-001 | Estimate for erection of 2.88KM 33KV new line from 132KV Suryapet SS to bifurcate the loads of 33KV HPCL Feeder (tapping point near Jayashanka polymers) emanating from 132/33KV Suryapet EHT SS in Chivemla section of Suryapet Division in Suryapet Circle under T&D Improvements to original works (Summer Action Plan works-2025). | 516481.92 | 10329.6384
8 | 36 | Others | T-2463-50-01-23-02-001 | Re routing of 4.320KM 11KV Machinapally feeder in Machinapally village in Nuthanakal mandal in Suryapet Division in Suryapet circle -under T&D works Ren. & Mod.Works | 180123 | 3602.46
9 | 37 | Others | T-2521-50-01-24-01-003 | Estimate Proposal is for erection of 1No. Additional 5MVA PTR in addition to the existing 1x8MVA+1X5MVA PTRs in 33/11KV Adivemla Sub-Station in Operation section J.R Gudem of Nagaram sub-division of Suryapet Division of Suryapet Circle - Under T&D PTR Augmentation works Summer action Plan-2026) | 459424.74 | 9188.4948
10 | 38 | Others | T-2530-50-01-23-03-001 | Estimate for erection of 2.92Km 33KV New feeder emanating from 132/33KV Nuthankal SS to Errapad X Road tapping point in Nuthankal village to 33KV/11KV Reddygudem SS to bifurcate 33KV Reddygudem feeder emanating from 132/33KV Thungathurthy SS due to 33KV Reddygudem feeder load is 303A in Maddirala section of Thungathurthy sub-division in Suryapet Division in Suryapet Circle under T&D Improvement to original works (Summer Action Plan works-2025). | 535439.25 | 10708.785
11 | 39 | Others | T-2432-50-01-12-02-001 | Bifurcation of overloaded 11KV Thimmapuram feeder emanating from 33/11KV Chandupatla SS by erection of 3.33KM new 11KV Modinipuram feeder from 33/11KV Durajpally SS which involves stringing of 2.7KM SCOH line & 0.63KM DCOH line with 55sq.mm AAA conductor over now proposed 11Mtrs & 9.1Mtrs PSCC poles along with bay extension and erection of 11KV feeder VCB at 33/11KV Durajpally SS in Chivmela section in Suryapet Rural subdivision in Suryapet Division of Suryapet Circle under T&D Improvements to original works | 583841 | 11676.82
12 | 40 | Others | T-2521-50-01-24-03-001 | Estimate for Erection of 1No. additional 5MVA PTR to the Existing 2X8MVA PTR'S thus making a total capacity of 1X5+2X8MVA at 33/11KV Nagaram Sub-Station in D.Nagaram Section of D.Nagaram Sub-division in Suryapet Division of Suryapet Circle under T&D PTR Augmentation works ( Summer Action Plan-2026). | 511351.22 | 10227.0244
13 | 41 | SC | T-2531-50-01-12-03-002 | Estimate for erection of 33KV Interlink line between 33KV Nelamarry feeder emanating from 132/33KV Munagala EHT SS to 33/11KV Bhakthalapuram SS feeding from 33KV G.Thirualagiri feeder emanating from 132/33KV Munagala EHT SS to provide alternate supply to 33/11KV Bhakthalapuram SS in Penpahad section of Suryapet division in Suryapet Circle - Under T&D Improvements to Original works (Under Summer Action Plan-2026) | 570745.65 | 11414.913
583841
Others

## PTR'S with cost (5)
Sl.No. | Sanction Date | WBS NO | 3KV Plinth | LV plinth
1 | 17.11.2025 | T-2521-50-01-24-01-002
2 | 17.11.2025 | T-2521-50-01-12-03-003
3 | 19.11.2025 | T-2521-50-01-12-03-002
4 | 19.11.2025 | T-2521-50-01-24-01-001
5 | 19.11.2025 | T-2521-50-01-24-01-003
6 | 19.11.2025 | T-2521-50-01-24-02-002
7 | 29.11.2025 | T-2521-50-01-24-03-001
8 | 06.12.2025 | T-2521-50-01-12-01-001